## Project Planner
AI in Education
[5 empty] | Period Highlight: | 7 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Collect materials | 1 | 2 | 1 | 2 | 70%
Plan | 2 | 1 | 2 | 1 | 100%
Finish research proposal | 1 | 1 | 1 | 1 | 100%
Get the tutor's review for research proposal | 3 | 1 | 3 | 1 | 100%
Update research proposal | 4 | 1 | 4 | 1 | 100%
Write literature review | 2 | 15 | 2 | 7 | 50%
Write and read AI in general | 2 | 4 | 2 | 4 | 90%
Gather studies about AI in education | 6 | 4 | 6 | 4 | 90%
Write analysis and hypothesis | 10 | 7 | 10 | 5 | 90%
Get the tutor's feedback for literature review | 17 | 1 | 17 | 1 | 0%
Update literature review | 18 | 1 | 18 | 1 | 0%
Prepare for experiment | 5 | 1 | 5 | 1 | 0%
List out all survey questions | 6 | 3 | 6 | 3 | 0%
Prepare for observation | 9 | 2 | 9 | 2 | 0%
List out all interview question | 5 | 2 | 5 | 5 | 0%
Get the tutor's feedback for preparation and question lists | 11 | 1 | 11 | 1 | 0%
Carry out the survey | 13 | 3 | 13 | 3 | 0%
Do the interview | 16 | 2 | 16 | 2 | 0%
Do the experiment | 13 | 3 | 13 | 3 | 0%
Do the observation | 13 | 7 | 13 | 7 | 0%
Collecting all results and analyze | 20 | 3 | 20 | 1 | 0%
Get tutor's feedback for the primary research | 24 | 1 | 24 | 1 | 0%
Do the assignment 1 | 25 | 5 | 25 | 3 | 0%
Submit assignment 1 draft | 30 | 1 | 30 | 1 | 0%
Assignment 1 final | 32 | 1 | 32 | 1 | 0%
Assignment 2 draft | 34 | 1 | 34 | 1 | 0%
Presentation | 35 | 1 | 35 | 1 | 0%
Assignment 2 Final | 36 | 1 | 36 | 1 | 0%